# ANNUAL PROGRAM & RECREATION ACTION PLAN 2021

For Year Time Period: January 2021 – December 2021

| Program Attendance | FY18 | FY19 | FY20 |
| --- | --- | --- | --- |
| Public Interpretive | 1,221 | 1,720 | 1,826 |
| Group Tour | 74 | 17 | 79 |
| Special Events ** | 984 | 1,187 | 2,027 |
| School Programs | 147 | 352 | 490 |
| Outreach Programs | 950 | 2,124 | 3,200 |
| TOTAL PROGRAM ATTENDANCE | 3,376 | 5,400 | 7,622 |

Current Dedicated Staff, Or Available Staff for Interpretive Efforts:

- Part Time Naturalist, Year Round, John Doe

- Site Manager, Jane Doe

- Assistant Site Manager, Ellen Graham

- Volunteers upon availability

Top Successes of 2020

- The seasonal naturalist offered outreach programs in the community in schools and the local library to try to gain more community support.

- “Ask the Naturalist” in the Museum was offered on various Saturday’s throughout the summer. This allowed the public to see the museum in a scheduled time frame as it had not been open regularly in the past.

- In 2020 the daily programs were posted on the Georgia State Parks website and they had not been promoted online in the past.

- A GoPher Mini Golf Tournament was offered as a new event with 36 participants and $100 in revenue.

- In FY20 the programs brought in $382 in Programming Revenue, a first in many years.

#### Program and Recreation Goals Achieved from 2020 Plan

#### Program Goals:

- Posted photos and program updates at least once each week on Facebook. Consolidated the many pages about the park into one official page and generated 354 likes.

- Added over 100 new guests to the monthly program mailing list via the program interest sign-up sheet at the Visitor Center and Bait Shop.

- Expanded winter programming by adding Night Sky Watch and Park Nights, City Lights Hike and increased frequency of Jr. Ranger Day Camps, New Manchester History Hikes, and Native American Heritage Hikes.

- Professionals in the following fields led programs at our park this year: botany, photography, stand up paddle boarding, Native American Culture and ornithology.

- Park and Friends Group purchased 6 new kayaks and trailer, as well as replacement seats and paddles.

Recreation Goals:

- Acquired four new Aqua Cycles and four new Stand Up Paddleboards to increase opportunities for visitors to explore the reservoir.

- Established and implemented new rental rates for all boats.  Each type of vessel is unique in Active to allow for revenue tracking.

#### Program and Recreation Goals for 2021

Program Goal 1:

Offer a minimum 1 Special Event program per month in 2021.

Actions needed to accomplish this goal

- Plan the Special Event schedule for all of 2021 by September of 2020.  (John)

- Advertise programs months in advance by on month in advance. (John)

- Post on GA State Parks website and online community event calendars as soon as the event dates are set by October 2020.

- Post to Facebook one month prior to each event with regular postings leading up to the event.

- Advertise with local newspapers per their deadline, between 1-2 weeks in advance.

- Post flyers at kiosks, office, posted on bulletin boards one month in advance.

- Arrange Friends volunteers to commit to each event with names and time commitments by asking 2 months prior to each event at the monthly meetings.  (John)

Program Goal 2:

Create & promote group program offerings (school, scout, general public), staff notebook, contract, etc.

Actions needed to accomplish this goal:

- Write the brochure, contract, rate sheet, calendar for group booking process by December 2020. (Ellen to email documents, John)

- Begin using the new group booking process and train all staff on group booking in January 2021 (John)

- Contact Dauset Trails to discuss partnership options for school field trips by November 2020.  (John)

- Contact school officials in the Spring of 2021 for permission to contact the Elementary school teachers in the Fall.  (John)

Program Goal 3:

Increase community outreach and involvement in park programs.

Actions needed to accomplish this goal

- Research local festivals and civic organizations by October 2020. (Ellen)

- Contact event officials and organization leadership to see how park can be involved by October 2020.  Ex.  Jackson Alive, Christmas Parade (Ellen)

- Create a display and load-n-go box for community events by November 2020. (John)

- Begin booking staff to attend community events and civic organization meetings at least 1 month in advance per their timeline.  (John & Ellen)

Program Goal 4:

Start a monthly homeschool day with activities.

Actions needed to accomplish this goal

- Determine activities and reliable schedule (John & Ellen)

- Reach out to local homeschool groups on Facebook, by email, etc. (John & Ellen)

- Advertise on Facebook, park website, and homeschool group sites (John & Ellen)

#### Recreation Goals for 2021

Recreation Goal 1:

Offer a monthly fitness program.

Actions needed to accomplish this goal

- Decide on dates/times for these programs by November 2020. (Jane)

- Advertise programs in advance by: (Jane/Clerk)

  - Post on GA State Parks website and online community event calendars as soon as dates are set for 2021.

  - Post to Facebook and Instagram one month prior to each program with regular postings leading up the program.

  - Include in monthly email newsletter

  - Advertise with local news media per their deadlines.

  - Post flyers at kiosk, Nature Center, bulletin boards, and etc. one month in advance.

- Contact local fitness instructors to serve as partners in this fitness program throughout 2021. (Jane)

Recreation Goal 2:

Develop an outdoors adventurer’s weekend long program that highlights all of the unique recreational activities (conservation hikes, archery, tree climbing, kayaking) that Panola/Atlanta has to offer on a quarterly basis. (Jane & John)

Actions needed to accomplish this goal

- Survey the local population to see what types of activities they would like to see included in an all exclusive outdoors adventurer’s weekend program and evaluate the different price bracket options for the different program options by December 2020. (Jane & John)

- Contact locally owned kayaking companies to discuss partnerships between Panola and their company to offer a component of the weekend that Panola cannot offer by December 2020. (John/Ellen)

- Solidify schedule (Jane & John)

- Advertise programs in advance by: (Jane & John)

  - Post on GA State Parks website and online community event calendars as soon as dates are set for 2021.

  - Post to Facebook and Instagram one month prior to each program with regular postings leading up the program.

  - Include in monthly email newsletter

  - Advertise with local news media per their deadlines.

## Special Event Programs Proposed for 2021

Special Events 2021 (Jane will coordinate all of these)

- Saturday, February 14, 2021:  I Love the Outdoors:  Annual Event, 1st year

- Saturday, March 20, 2021:  Spring Fling:  2nd year

- Saturday, April 3, 2021:  Birding By Ear:  2nd year

- Saturday, May 23, 2022:  Mini Golf Tournament:  Annual Event, 2nd year

- Saturday, August 28, 2021:  Full Moon Hike program:  1st year

- Saturday, September 11, 2021:  Fall Flowers:  3rd year

- Saturday, October 23, 2021:  Sock Hop:  Annual Event, 2nd year

- Saturday, November 27, 2021:  Storytime with Santa:  Annual Event, 5th year

Required State-Wide Special Events:

- First Day Hike – January 1, 2021:  Hike in the New Year:  Annual Event, 7th year

- Girl Scouts Love State Parks –  September 11 & 12, 2021

  - Wilderness Survival Skills Workshop for Scouts, 2nd year

- Your State Park Day – September 25, 2021:  Painting Picnic Tables Project:  7th year

- Junior Ranger Day Camp:  June 14-18, 2021:  2nd year

Recommendations for strengthening Special Events 2021:

- Improve advertising for all events  (John)

  - Use Facebook, park website, flyers, local newspapers, community event calendars

- Utilize volunteer help more efficiently (Ellen & John)

  - Assign specific tasks to volunteers

  - Schedule program help in advance (names, dates, times)

- Make a Special Event notebook tabbed by each event to keep flyers, registration sign up details and notes after each event to make planning for 2021 easier.  (John & Ellen)

Program goals to target audiences not currently engaging:

- Schedule volunteer work days to develop gardens to attract people in the local community to engage garden clubs and garden hobbyists. (Jane, Ellen & John)

- By keeping a consistent schedule with the museum open, the park will be able to promote being the “oldest state park in the nation” to attract history enthusiasts.  (John)

- See how the consistent program schedule offering attracts the African American population who is visiting for day use but not for ranger-led activities/programs.  Revisit after a year to see if the programs offered should be altered.  (John)

Passive Programs and Interpretive Projects Proposed for 2021

Passive Programs or Interpretive Project Goal 1:

Renovate two bulletin boards

Actions needed to accomplish this goal

- Replace backing, Plexiglas covers, repaint, by March 2021.  (Jane, volunteers)

- Update flyers each season/quarterly and the borders/decorations.  (John, Jane, Ellen)

Passive Programs or Interpretive Project Goal 2:

Improve existing Lake Trail guide.

Actions needed to accomplish this goal

- Add additional information and points of interest by March 2021 (John)

- Replace trail signs to correspond with new trail guide by April 2021 (John, Jane, Ellen)

Future Interpretive or Recreational Considerations:

- Develop Hotel History Hike

- Research locations of hotels

- Install signs at locations including cost of room, number of rooms, etc.

- Museum renovation/improvement

- Update information (some displays are misspelled, others are incorrect)

- Add information (Butts County Historical Society)

- Pursue full time interpretive ranger to allow increased programming and special events

- Market Indian Springs, High Falls, and Jarrell Plantation as a unit for field trips, group programs, etc.

Programming Needs From Site Budget

| Item | Quantity | Price per item | Total expense |
| --- | --- | --- | --- |
| arrows | 2 dozen | $20.00 | $40.00 |
| Glow sticks (for kayaks on full moon paddles) | 60 bags | $1.00 | $60 |
| Astronomy binoculars | 8 | $60 | $480 |